NIDHI CATERING Order Management System · Waterfall Execution Plan DEVELOPER REFERENCE

| TOTAL PHASES 8 (Phases 0 – 7) | EXECUTION MODEL Waterfall + Iterative | SUPPORT WINDOW 2 Months Post Go-Live | AUDIENCE Developer (Internal) |
| --- | --- | --- | --- |

PARALLEL EXECUTION NOTE (Phases 0, 1 & 2) Phases 0, 1, and 2 run simultaneously. Phase 3 begins only after all three complete. Phases 5 and 7 are iterative (non-linear).

| PHASE 0 · PRE-KICKOFF INPUTS [ PARALLEL ] |  |  |  |  |
| --- | --- | --- | --- | --- |
| # | Task / Step | Technical Details | Output / Deliverable | Status |
| 0.1 | Website Menu Data → Excel | Parse website menu into structured Excel sheet. Client validates extracted items, pricing, and fields. No new classification required. | Validated menu Excel file | ☐ To Do |
| 0.2 | Confirm Fixed Scope | Lock in: Desktop-only web UI; PDF quote delivery only; plan-ahead window = 7 days; post-go-live support = 2 months. | Signed scope assumption doc | ☐ To Do |
| 0.3 | AI Account & Ownership Setup | Client opens Anthropic/OpenAI account on their credit card. Dev integrates via API keys stored in env vars. Usage costs borne by client. | API keys available in .env | ☐ To Do |
| 0.4 | Database Choice | Select DB based on convenience and hosting constraints: SQLite / MySQL / PostgreSQL. Keep DB layer abstracted (Prisma ORM) to allow early switching. | DB technology decision logged | ☐ To Do |
| EXIT CRITERIA → Menu Excel extracted and client-validated → AI account created and API keys provided → Database technology decided |  |  |  |  |
| PHASE 1 · REQUIREMENT FREEZE & DESIGN [ PARALLEL ] |  |  |  |  |
| # | Task / Step | Technical Details | Output / Deliverable | Status |
| 1.1 | CRD — Requirement Freeze | Confirm all form fields, admin review/edit flow, PDF layout expectations, email confirmation step. Produce CRD v1.0 document. | CRD v1.0 signed off by client | ☐ To Do |
| 1.2 | Technical Design | UI screen wireframes + navigation map; REST API endpoints and workflow; DB schema (orders, items, customers, events, metadata); PDF generation library choice; email service (Resend/SendGrid). | Architecture doc + screen flow diagram | ☐ To Do |
| EXIT CRITERIA → CRD v1.0 reviewed and signed off → Architecture diagram and screen flow locked |  |  |  |  |
| PHASE 2 · APP FOUNDATION SETUP [ PARALLEL ] |  |  |  |  |
| # | Task / Step | Technical Details | Output / Deliverable | Status |
| 2.1 | Project Scaffold | Initialize repo/app structure (Next.js or equivalent). Configure environment model (.env.example). Produce build & run instructions (ZIP-deployable for client's engineer). | Runnable scaffold committed to repo | ☐ To Do |
| 2.2 | Database Setup | Implement chosen DB. Create schema + migration/init scripts. Seed reference data only if required (otherwise rely on menu Excel import flow). | DB schema created, migrations working | ☐ To Do |
| 2.3 | AI + Email Integration | Wrap Anthropic/OpenAI client. Integrate email service (Resend or SendGrid). All credentials via environment variables — no hard-coding. | AI + email connectivity validated end-to-end | ☐ To Do |
| EXIT CRITERIA → App runs locally with stub data end-to-end → DB reads and writes verified → AI response and email delivery confirmed |  |  |  |  |
| PHASE 3 · CORE FEATURE DEVELOPMENT [ SEQUENTIAL — WATERFALL ] |  |  |  |  |
| # | Task / Step | Technical Details | Output / Deliverable | Status |
| 3.1 | Order Intake UI (Desktop) | Desktop-first web form: item selection + quantity + notes; customer/event fields; client-side validation (Zod or equivalent). | Functional order intake screen | ☐ To Do |
| 3.2 | Backend Order Processing | Server-side validation. Save order + line items to DB. Persist advance payment, delivery type, location, equipment, notes. | Order data persisted in DB correctly | ☐ To Do |
| 3.3 | Quote Calculation + Admin Edit | Auto-compute line totals and grand total. Admin interface to edit line items and totals before finalizing. Audit trail of changes. | Quote editor functional with correct totals | ☐ To Do |
| 3.4 | PDF Quote Generation | Template-driven PDF generation. Include: customer/event details, itemized table, totals, branding. Library: pdfkit / react-pdf / puppeteer (TBD in Phase 1). | PDF quote generated correctly per order | ☐ To Do |
| 3.5 | Email Delivery Workflow | Owner enters customer email. AI or template generates email body. PDF attached automatically. Owner reviews and confirms before send. Email + send timestamp logged. | End-to-end email flow with PDF attachment | ☐ To Do |
| EXIT CRITERIA → Full flow works: form → DB → PDF → email reliably → Admin edit and quote finalization verified |  |  |  |  |
| PHASE 4 · WEEKLY PLAN-AHEAD MODULE [ SEQUENTIAL — WATERFALL ] |  |  |  |  |
| # | Task / Step | Technical Details | Output / Deliverable | Status |
| 4.1 | Plan-Ahead Query | DB query: retrieve all orders for the next 7 days. Sort and group by date. No complex scheduling engine — straightforward data retrieval. | Correct order list for next 7 days | ☐ To Do |
| 4.2 | Output Formatting | Format results into predefined category buckets (Appetizers / Main / Dessert / etc.) and Veg / Non-Veg splits. Uses existing menu classification from Excel. Presentation logic only. | Formatted plan-ahead data set | ☐ To Do |
| 4.3 | Kitchen-Friendly UI + Print | Clean desktop view of the weekly plan. Print-optimised CSS layout. Export / Print button. Output usable directly in kitchen workflow. | Printable weekly plan view ready | ☐ To Do |
| EXIT CRITERIA → Kitchen staff can generate and print 7-day plan in one click |  |  |  |  |
| PHASE 5 · TESTING [ ITERATIVE ] |  |  |  |  |
| # | Task / Step | Technical Details | Output / Deliverable | Status |
| 5.1 | Functional Testing | Test: form submission; admin edits; PDF generation accuracy; email sending and confirmation behaviour; plan-ahead output correctness. | Functional test checklist signed off | ☐ To Do |
| 5.2 | Edge & Negative Testing | Scenarios: missing/invalid fields; large item counts; multiple orders on same day; delivery vs pickup variations; empty state handling. | Edge case test results documented | ☐ To Do |
| 5.3 | Bug Fix Cycles | Fix → retest → validate loop until stable. All critical/high issues resolved before Phase 6. | Zero open critical or high severity issues | ☐ To Do |
| EXIT CRITERIA → No critical or high severity issues open → All functional scenarios pass |  |  |  |  |
| PHASE 6 · PACKAGING, DELIVERY & GO-LIVE [ SEQUENTIAL — WATERFALL ] |  |  |  |  |
| # | Task / Step | Technical Details | Output / Deliverable | Status |
| 6.1 | Package Delivery | Ship ZIP archive containing: full app source; .env.example (config template); setup instructions; DB init / migration scripts; build and run steps. | ZIP package delivered to client's engineer | ☐ To Do |
| 6.2 | Deployment Support | Light Q&A with client's engineer during Hostinger deployment. Provide smoke test checklist to verify post-deploy functionality. | App deployed on Hostinger, smoke test passed | ☐ To Do |
| EXIT CRITERIA → App successfully deployed on client Hostinger environment → Client sign-off received |  |  |  |  |
| PHASE 7 · POST-DELIVERY SUPPORT [ ITERATIVE / ONGOING ] |  |  |  |  |
| # | Task / Step | Technical Details | Output / Deliverable | Status |
| 7.1 | Issue Tracking | Log and triage: email delivery issues, PDF formatting bugs, data inconsistencies, UI errors reported by client. | Issues tracked in shared log | ☐ To Do |
| 7.2 | Bug Fixes | Fixes for issues within original scope only. No new feature requests. Each fix validated by client before closing. | Bugs resolved and confirmed | ☐ To Do |
| 7.3 | Operational Assistance | Minor config help, usage clarifications for owner/staff, environment variable or hosting adjustments if needed. | Client and staff able to operate independently | ☐ To Do |
| EXIT CRITERIA → 2-month support window complete → No outstanding critical issues → Project formally closed |  |  |  |  |